## Sheet1
User Story ID | User Story Description | Acceptance Criteria | Feature | Component | Story Points
US_01 | As a campaign manager, I want to create new campaigns with a target amount and deadline | System allows manager to set target and deadline; Contract deploys successfully; Manager automatically becomes campaign owner | Campaign Creation | Smart Contract | 25
US_02 | As a supporter, I want to contribute funds to a campaign | Contribution ≥ min amount; Contributor stored; Total raised updates automatically | Campaign Contribution | Smart Contract | 25
US_03 | As a contributor, I want to get a refund if the goal is not met before the deadline | Refund available only after deadline; Only contributors can request refund; ETH refunded equals original contribution | Refund Processing | Smart Contract | 25
US_04 | As a manager, I want to create spending requests for raised funds | Manager creates request with description, value, recipient; Default state: not completed | Request Creation | Governance | 20
US_05 | As a contributor, I want to vote on spending requests | Only contributors can vote; Each contributor can vote once; Vote count updates accurately | Request Voting | Governance | 22
US_06 | As a manager, I want to release funds after majority approval | Only manager executes payments; Majority approval required; ETH transferred; Request marked completed | Fund Release | Governance | 25
US_07 | As a user, I want to view all campaigns with details | Display campaign list; Show goal, deadline, raised amount; Reflect status dynamically | Campaign Listing | Data Display | 20
US_08 | As a user, I want to see campaign status (Active, Successful, Failed) | Status updates based on raised amount and time; Proper label displayed | Campaign Status | Data Display | 20
US_09 | As a system, I want to validate minimum contribution to ensure fairness | Reject transactions < min amount; Display error message | Validation Logic | Contract Validation | 10